## Instructions
Using the Status tracker - At the end of each week, update the status of all activities completed during the week. - The status tracker shown in this worksheet is an example tracker (values filled are during the middle of the week). - Fill in hours spent on each activity during the current week. - If 5 team members each spent an hour, that counts as 5 hours. - Fill in time for activities not fully completed ("ongoing") as well, then update these values during following weeks. - During the planning phases, identify the activities to be done during each week. - If you spend time on an activity not listed in the tracker, add the activity and list actual hours (need not fill in estimated hours if you didn't estimate it up front). - For new activities, identify the type of activity - documentation, coordination, estimation etc. - At the end of each week, plan ahead for the following week Identify people responsible for each activity. - Estimate the hours needed for the activity - Error in estimation is calculated using a formula that’s already applied.
PROJECT NUMBER | SSAD 35
PROJECT NAME | Object Detection & Tracking against 3D models
PROJECT MENTOR (sponsor) | Anil Kumar Upadhyay
TEAM MEMBERS | AadilMehdi Sanchawala
Antony Martin
Priyank Modi
Rohan Chacko

## Status
PROJECT NUMBER | SSAD 35
PROJECT NAME | Object Detection & Tracking against 3D models
PROJECT MENTOR (sponsor) | Anil Kumar Upadhyay
Activity Name | Type | Responsible | Estimated Team Hours | Actual Hours | Status | Comments | Estimation error | Estimation error %
Week 1 (August 6- August 12)
Fix meeting with client | Coordination | Rohan Chacko | 0.5 | 0.3 | Done |  | 0.2 | 66.6667
GIT Repository setup | Preparation | AadilMehdi | 0.5 | 0.5 | Done |  | 0 | 0
Client meeting | Coordination | Priyank Modi | 2 | 1.5 | Done |  | 0.5 | 33.3333
Pushing necessary documents onto repository | Documentation | Antony Martin | 1 | 2 | Done |  | -1 | 50
Prepare project pipeline | Design | Rohan & Aadil | 2 | 2.5 | Done |  | 0.5 | 20
Week 2 (August 13 - August 19)
Prepare project pipeline | Preparation | Rohan & Aadil | 2 | 2.5 | Done |  | 0.5 | 20
Gitlab Structure Setup | Preparation | AadilMehdi | 0.25 | 0.25 | Done |  | 0 | 0
Team Meeting | Coordination | All | 1.5 | 2 | Done |  | -0.5 | 25
Status tracker update | Documentation | Rohan | 0.25 | 0.25 | Done |  | 0 | 0
TA Mentor Meeting | Coordination | All | 1.5 | 1 | Done |  | 0.5 | 50
Client meeting | Requirements | All | 1.5 | 1.5 | Done |  | 0 | 0
Learn required concepts | Preparation | All |  |  | Ongoing
Experiment with already implemented programs | Preparation | All | 4.5 | 6.5 | Done |  | -2 | 30.7692
Week 3 (August 20 - August 26)
Experiment with already implemented programs | Preparation | All | 4.5 | 6.5 | Done |  | -2 | 30.7692
Client meeting to finalise requirements | Preparation | All | 1.5 | 1.5 | Done |  | 0 | 0
Reading through research papers | Preparation | All | 15 | 20 | Done |  | -5 | 25
Developing prototypes Iter.1.0 | Development | All | 10 | 12 | Done | Prototype Iter1 started | -2 | 16.6667
Learning required softwares/implementations | Preparation | All | 12 | 10 | Ongoing |  | 2 | 20
Week 4 (August 27 – September 2)
Learning required softwares/implementations | Preparation | Antony&Priyank | 8 | 7 | Ongoing |  | 1 | 14.2857
Developing prototypes Iter.1.1 | Development | Rohan&Aadil | 9 | 10 | Done |  | -1 | 10
Testing prototypes of Iter.1.0 & Iter.1.1 | Testing | Rohan&Aadil | 4 | 4 | Done |  | 0 | 0
Team Meeting | Coordination | All | 4 | 6 | Done | Prototype Iter1 over | -2 | 33.3333
Week 5 (September 3 – September 9)
Understand already implemented programs | Preparation | All | 4 | 4 | Done |  | 0 | 0
Developing prototypes Iter.2.0 | Development | Rohan,Aadil&Priyank | 9 | 12 | Ongoing | Prototype Iter2 started | -3 | 25
Identifying drawbacks in prototype | Testing | Antony | 3 | 3 | Done |  | 0 | 0
Developing prototypes Iter.2.1 | Development | All |  |  | Ongoing
Week 6 (September 10 – September 16)
Developing prototypes Iter.2.1 | Development | Rohan,Aadil&Priyank | 6 | 8 | Ongoing |  | -2 | 25
Receive mesh models from the client | Coordination | Aadil, Rohan, Antony | 4 | 4 | Done |  | 0 | 0
Status tracker update | Documentation | Aadil | 0.5 | 0.5 | Done |  | 0 | 0
Week 7 (September 17 – September 23 )
Team Meeting | Coordination | All | 6 | 6 | Done |  | 0 | 0
Experimenting with Mesh Models | Preparation | Aadil, Rohan | 7 | 8 | Done |  | -1 | 12.5
Identifying obstacles in extending current approach to Mesh Models | Preparation | Aadil, Rohan | 10 | 14 | Done |  | -4 | 28.5714
Week 8 (September 24 – September 30 )
Meeting with the client | Coordination | All | 2 | 1.5 | Done |  | 0.5 | 33.3333
Identifying new algorithms to map the mesh models to the scene keypoints | Preparation | Rohan, Aadil, Priyank | 9 |  | Ongoing
Reading through research papers to understand mapping issues | Preparation | Rohan, Aadil | 8 |  | Ongoing
Working with MeshLab to extract projections from the mesh models | Development | Aadil, Priyank, Antony | 6 |  | Ongoing
Learning to use Blender | Preparation | Aadil & Priyank | 4 | 7 | Done |  | -3 | 42.8571
Testing Sobel and Canny Edge Detectors | Preparation | All | 3 | 8 | Done |  | -5 | 62.5
Week 9(October 1 – October 7)
Team Meeting | Coordination | All | 6 | 6 | Done |  | 0 | 0
Creating the line templates from the mesh models | Development | Aadil & Priyank | 2 | 4 | Done |  | -2 | 50
Script to extract frames out of the video for line templates | Development | Aadil | 1 | 1 | Done |  | 0 | 0
Extract edges from video by converting to grayscale and using Canny Edge detector | Development | Rohan & Antony | 3 | 6 | Done |  | -3 | 50
Testing accurate matching by adjusting parameters | Coordination | All | 6 | 8 | Done
Matching the line template of model in the video stream | Development | Rohan & Antony | 2 | 4 | Done |  | -2 | 50
Picking the best detection out of the probable detections based on the min and max parameters | Development | Rohan, Antony | 1 | 2 | Done |  | -1 | 50
Logging the postion and time into a file | Development | Rohan | 1 | 1 | Ongoing |  | 0 | 0
Presentation design | Design | Priyank Modi | 2 | 2 | Done |  | 0 | 0
Writing bash scripts for testing | Development | Aadil & Priyank | 1 | 2 | Ongoing |  | -1 | 50
Week 10(October 8 – October 15)
Code Documentation | Development | Priyank & Rohan | 1 | 1 | Done |  | 0 | 0
Added functionality of taking video as argument | Development | Aadil | 1 | 1 | Done |  | 0 | 0
Added more templates and training videos | Development | Aadil & Priyank | 2 | 2 | Done |  | 0 | 0
Figuring out problems with processing speed | Coordination | All | 3 | 3 | Ongoing |  | 0 | 0
Added video resolution reduction in main module | Development | Aadil | 2 | 2 | Done |  | 0 | 0
Added settings for 240p | Development | Rohan | 1 | 1 | Done |  | 0 | 0
Code Refactoring | Development | All | 2 | 2 | Ongoing |  | 0 | 0
Week 11(October 23 - October 30)
Updated design document | Development | All | 2 | 2 | Done |  | 0 | 0
Added video writer | Development | Aadil | 3 | 3 | Done |  | 0 | 0
Added more training videos | Development | Priyank | 1 | 1 | Done |  | 0 | 0
Extended code for 2 objects | Development | Antony | 1 | 1 | Done |  | 0 | 0
Displaying name of object around bounding box | Development | Aadil | 2 | 2 | Done |  | 0 | 0
Added fps, elapsed time display | Development | Rohan | 2 | 2 | Done |  | 0 | 0
Client meeting | Coordination | All | 1 | 1 | Done |  | 0 | 0
Week 12(October 31 - November 6)
Added functionality for handling multiple objects | Development | Antony & Priyank | 2 | 2 | Ongoing |  | 0 | 0
Team Meeting | Coordination | All | 2 | 2 | Done |  | 0 | 0
Discussed possibility of using SVM for increasing speed | Coordination | All | 1 | 1 | Done |  | 0 | 0
Modifeied template generator | Development | Aadil | 2 | 2 | Done |  | 0 | 0
Code linting | Development | Rohan | 3 | 3 | Done |  | 0 | 0
Multi threading for all objects | Development | Rohan | 3 | 3 | Done |  | 0 | 0
Added progress bar functionality | Design | Aadil | 2 | 2 | Done |  | 0 | 0
Font size for the label increased | Development | Priyank and Rohan | 0.2 | 0.2 | Done |  | 0 | 0
Completed functionality for multiple objects | Development | Priyank, Antony | 2 | 4 | Done |  | -2 | 50
Week 13(November 7 – November 10)
Wrote test scripts | Testing | Priyank | 5 | 5 | Done |  | 0 | 0
Fixed bugs found | Development | Aadil and Rohan | 3 | 6 | Done |  | -3 | 50
Team Meeting | Coordination | All | 3 | 3 | Done |  | 0 | 0
Added progress bar for template generator | Interfaces | Priyank | 1 | 1 | Done |  | 0 | 0
Presentation design | Design | Priyank | 2 | 2 | Done |  | 0 | 0
Cleaned up the old templates and generated new ones | Development | Aadil and Priyank | 1 | 2 | Done |  | -1 | 50
Resolving merge conflicts | Development | Rohan | 2 | 2 | Done |  | 0 | 0
Resolved accuracy issues and np.line bugs | Development | Aadil and Antony | 2 | 4 | Done |  | -2 | 50
Shot presentation video | Delivery | All | 4 | 4 | Done |  | 0 | 0
Video editing | Design | Priyank | 3 | 3 | Done |  | 0 | 0